## Table 1
KEBBI STATE BUSINESS ENABLING REFORMS ACTION PLAN 2024 | [11 empty] | PROGRESS REPORT
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | List of Private Sector Contributors | Estimated cost | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
1 | Improved transparency in Land Administration and Land-based Investment Process | (i) Enhance the administration and management of land in Kebbi State; (ii)Improve transparency of property registration | Publish the process for obtaining CofO including all relevant MDAs, time frames and costs on the State official website | Provide public access to detailed information on the process of obtaining Certificate of Occupancy in Kebbi State and thereby enhance transparency and efficiency of land administration and property | Individual and corporate owners of land and property | Ministry of Land, Housing and Urban Planning, Kebbi GIS | Ministry of Finance, Kebbi State Internal Revenue Service (KIRS) | Kebbi Chamber of Commerce and Industry Kebbi State Market Traders Association Nigerian Association of Small and Medium Enterprises | Not Applicable | 2024-01-01 | 2024-02-28 | Done This reform has enhanced the administration and management of land in Kebbi State | The process for obtaining CofO has been published on the state website | Not applicable
|  |  | Publish the process for obtaining construction permit including all relevant MDAs, time frames and costs on the State official website | Provide public access to detailed information on the the process of obtaining Constrution permits in Kebbi State. | Individual and corporate owners of land and property | Ministry of Land, Housing and Urban Planning, Kebbi GIS | Ministry of Finance, KIRS |  | Not Applicable | 2024-01-01 | 2024-02-28 |  | The process for obtaining construction permit has published on the state website
|  |  | Digitize and index CofOs registered from 1 January 2012 to December 31, 2024 | Digitize and archive 75% of CofO | Individual and corporate owners of land and property | Ministry of Land, Housing and Urban Planning, Kebbi GIS |  |  | N400,000,000 | 2024-01-01 | 2024-12-31 |  | A digital archive has been created and the 80% of CofOs digitally archived
|  |  | Issue Executive Order on FRILIA | The Executive Order provides a legal basis for the insitution of FRILIA practices in Kebbi State | Investors, farmers and land owners | Ministry of Justice | Ministry of Land, Housing and Urban Planning, Ministry of Justice |  | Not Applicable | 2024-01-01 | 2024-01-10 |  | An Executive Order establishing FRIILIA has been passed
|  |  | Institute the Framework for Responsible and Inclusive Land Intensive Agriculture (FRILIA) | (i) Establish a Steering Committee on FRILIA (ii) Create an interministeral consultative platform to address FRILIA challenges | Investors, farmers and land owners | Ministry of Land, Housing and Urban Planning, Ministry of Agriculture and Natural Development, Kebbi GIS, | Ministry of Justice, Ministry of Finance, Ministry of Commerce, Industry and Tourism, KIRS, Kebbi State Investment Promotion Agency, Office of the Surveyor-General, |  | N40,000,000 | 2024-01-01 | 2024-12-31 |  | The FRILIA Steering Committee has been successfully established and inaugurated, with membership drawn from relevant MDAs, civil society, and traditional institutions. Efforts are now focused on operationalising the interministerial consultative platform, with preliminary stakeholder mapping and coordination frameworks underway | Finalise and launch the interministerial consultative platform.
2 | Improved regulatory framework for private investment in fiber optic infrastructure | Minimize high cost of infrastructure services as incentive for providing efficient broadband service in Kebbi State | Amend existing legislation or regulations towards limiting aggregate fees for broadband to a maximum of NGN145 per meter | Provide legal basis for limiting costs associated with laying of fibre optic cable in the State | Telecommunication operators, business owners and digital natives | Ministry of Land, Housing and Urban Planning, Kebbi Urban Development Agency (KUDA) | Ministry of Works and Transport, KIRS, Kebbi State Environmental Protection Agency (KESEPA) |  | Not Applicable | 2024-01-01 | 2024-12-31 | Done This refrom is the first step in bringing high speed internet to kebbi State | A regulation to waive right of way fees has been passed into law by the Kebbi Ueban Development Agency | Not applicable
|  |  | Publish on state website procedures, cost and timeline related to obtaining Right of Way (ROW) | Enhance transparency in obtaining Right of Way approvals | Telecommunication operators, business owners and digital natives | Ministry of Land, Housing and Urban Planning, Kebbi Urban Development Agency (KUDA) | Ministry of Works and Transport, KIRS, Kebbi State Environmental Protection Agency (KESEPA) |  | Not Applicable | 2024-01-01 | 2024-12-31 |  | The process for application of ROW has been published on the state official website
3 | Develop an effective framework for Public Private Partnerships | Establish effective Public-Private Partnership (PPP) framework for the state | Establish a PPP unit within Kebbi Investment Promotion Agency (KIPA) | Issue regulation on PPP pursuant to KIPA law | Investors | KIPA | Ministry of Commerce, Industry and Tourism |  | Not Applicable | 2024-01-01 | 2024-06-30 | Done This reform has positioned Kebbi state for investment | A regulation has been issued on PPP to establish a unit within KIPA
|  |  | Amend KIPA law to give it legal backing to lead PPP transactions | Enact and implement a State Public Private Partnership Law designating KIPA as lead agency for PPP facilitation | Investors | KIPA | Ministry of Commerce, Industry and Tourism |  | Not Applicable | 2024-01-01 | 2024-01-31 |  | A law has been passed mandating KIPA as the lead agency for the facilitaion of PPP
|  |  | Create PPP disclosure portal of the pipeline projects | KIPA to create a PPP disclosure portal on her website and state official website. | Investors | KIPA | Ministry of Commerce, Industry and Tourism |  | N10,000,000 | 2024-01-01 | 2024-03-31 |  | A disclosure portal has been developed and launched https://kebbippp.ng/
|  |  | Organise periodic information sessions annually for investors | Engage with stakeholders at least twice in 2024 with a view to removing bureaucratic constraints in the business environment in Kebbi State | Investors | KIPA | Ministry of Commerce, Industry and Tourism, Ministry of Budget and Economic Development |  | N7,000,000 | 2024-01-01 | 2024-12-31 |  | Two investor/stakeholder meetings were held to engage on how to improve the business environment in the state | An invesment summit is being planned to bring larger awarenes to invesment opportunities in the state
|  |  | Institute aftercare and retention program | Investors require aftercare support and KIPA is expected to dedicate resources and time to providing necessary support to investors | Investors | KIPA | Ministry of Commerce, Industry and Tourism |  | N1,600,000 | 2024-01-01 | 2024-12-31 | Ongoing The Aftercare Unit when fully operational aims to help fascilitate investor retention in Kebbi state | Initial steps have been taken by KIPA to identify the needs of existing investors and lay groundwork for the aftercare program. However, a formalised aftercare and retention structure is still being developed, with staff capacity and stakeholder collaboration currently under review. | Finalise the framework for investor aftercare services, including feedback and complaint resolution channels. Allocate dedicated personnel within KIPA to manage investor relations and provide tailored support.
|  |  | Develop a Foreign Direct Investment (FDI) Plan | Identify global FDI trends and target potential investors to invest at least $15 million in the State in order to generate wealth and jobs for the citizens of the State | Investors, MSMEs | KIPA | Ministry of Commerce |  | 500000 | 2024-01-01 | 2024-06-30 | Ongoing | The kebbi state export strategy was developed to guide, ongoing talks with potential investors in viable sectors in the state | Steps needed to complete
|  |  | Establish State Project Facilitation Fund with a minimum funding of 3% of the total pipeline estimated capital investment | Catalyze public private investments with facilitation fund and ensure that feasibility study on at least one PPP project is completed | Investors | Ministry of Finance, Ministry of Budget and Economic Development | Ministry of Commerce, Industry and Tourism, KIPA |  | Not Applicable | 2024-01-01 | 2024-06-30 | Ongoing | A project facilitation fund has been establised with a business plan for the fund under development to facilitate utilization of the fund | Steps needed to complete
4 | Financing Small and Medium Enterprise and Industrial Development | Increase efficiency in governance and improve revenue generation | Establish Kebbi State Asset Management Company (KESAMCO) such that the State begins to generate at least N25 million from State asset in 2024 | The asset management company will facilitate long-term credit financing for industrial development and creates an Asset Register to champion the management of all government assets profitably | MSMEs, Investors | Ministry of Justice | Ministry of Budget & Economic Planning, Ministry of Commerce, Industry and Tourism, Ministry of Finance |  | N35,000,000 | 2024-01-01 | 2024-06-30 | Ongoing | Initial groundwork has commenced, with the reform currently in the early stages of planning and institutional alignment. Key deliverables such as the formal creation of KESAMCO and the compilation of the Asset Register are still underway | Complete the legal and administrative processes for establishing KESAMCO. Initiate the asset identification and valuation process to build the Asset Register.
5 | Simplification of State and Local Business Tax Regimes | This reform is aimed at making it easy to understand and make payment for tax in Kebbi State | Subsume all business-related local government charges/fees/taxes into a consolidated demand notice | Generate harmonized Demand Notice | Micro, Small and Medium Entreprises (MSMEs) and investors | KIRS | Ministry of Finance, Ministry of Local Government and Chieftancy Affairs, Ministry of Justice, Ministry of Budget and Economic Development |  | Not Applicable | 2024-01-01 | 2024-08-30 | Ongoing -This reform will making tax collection seamless and transparent | A consolidated and harmonized demand notice has been successfully developed and issued, effectively integrating all business-related taxes, charges, and levies across local governments into a single document for ease of understanding and payment. | Steps needed to complete
6 | Develop Intermodal transport system | This reform is targeted at introducing rail in the State transport infrastructure towards a more efficient and cost-effective movement of goods | Develop electronic platform for collection of taxes,levies and fees from businesses and generate automated e-receipt for State and Local Governments | Electronic platform will automate consolidated payment for relevant fees and increase adoption of e-payment of taxes | MSMEs | Kebbi State Internal Revenue Service, Ministry of Local Government and Chieftancy Affairs, | Ministry of Finance, Ministry of Justice, Ministry of Budget and Economic Development |  | N900,000,000 | 2024-01-01 | 2024-12-31 | ongoing Impacts | The IRS arm of the Kebbi state government has developed a portal for the payment of tax and levies | Make the system more seamless
|  |  | Conduct feasibility study and design of rail from Minna to Kebbi | Link and integrate Kebbi State to the national railway infrastructure to ease movement of persons, goods and service | MSMEs | KIPA, Ministry of Works and Transport | Ministry of Finance, Ministry of Budget and Economic Development |  | N100,000,000 | 2024-01-01 | 2024-12-31 | Ongoing Impacts | Preliminary engagements with the Federal Ministry of Transportation and relevant railway authorities have commenced. A technical team has been constituted to oversee the feasibility assessment. Initial desk review and route mapping exercises are underway, with field-level technical assessments expected to commence in Q3 2025. Budgetary provisions are being considered for inclusion in the 2026 fiscal year. | What are the next steps needed to complete the ongoing activity?
7 | Quick determination of commercial disputes | This reform area will improve the State Judiciary and strengthen access to an efficient commercial justice system | Develop monthly performance reports for small claims courts from inception of the courts to December 2024 | The Judiciary will provide monthly performance reports on the activities of the small claims court on a monthly basis | MSMEs | Kebbi State Judiciary | Ministry of Justice |  | Not Applicable | 2024-01-01 | 2024-12-31 | Done Impacts | The State Judiciary has launched a dedicated website featuring operational details and performance records (disposition indicators and execution judgements) of the small claims courts. Reports for the year 2024 have already been uploaded, ensuring transparency and public access to judicial performance data. | Maintain consistent monthly updates on the Judiciary website. Expand reporting scope to include case timelines, resolution rates, and user satisfaction metrics. Institutionalise a digital dashboard to track commercial case performance in real time.
|  |  | Publish on the State Judiciary website monthly performance reports for small claims courts. | The Judiciary will publish performance reports on the activities of the small claims court on a monthly basis | MSMEs | Kebbi State Judiciary | Ministry of Justice |  | Not Applicable | 2024-01-01 | 2024-12-31
|  |  | The state judiciary's small claims court performance report will include the time to disposition indicator showing that cases are disposed of within 60 days | The small claims court magistrates are to ensure at least 50% performance achievement | MSMEs | Kebbi State Judiciary | Ministry of Justice |  | Not Applicable | 2024-01-01 | 2024-12-31
|  |  | The small claims court performance report will also include execution indicator showing the execution of judgments within 30 days | The small claims court magistrates are to ensure at least 50% performance achievement | MSMEs | Kebbi State Judiciary | Ministry of Justice |  | Not Applicable | 2024-01-01 | 2024-12-31